## PIF
A. | PROJECT INFORMATION
1 | Project Title: |  |  | Lower Santa Margarita River IPR Pilot Project
2 | Project Sponsor(s): |  |  | Fallbrook Public Utility District (Fallbrook PUD)
3 | Eligible Applicant Type:
4 | IRWM Project Region(s): |  |  | San Diego IRWM Region
5 | Does the project provide benefits directly to a Disadvantaged Communities (DAC) and/or Economically Distressed Areas (EDA) (minimum 75% by population or geography)?
|  | Yes | No | If yes, please complete D.8 and/or D.9. Show on map if applicable.
6 | Is the Project Sponsor a Tribe, or does the project provide benefits to a Tribe (minimum 75% by population or geography) as defined by Proposition 1?
|  | Yes | No | If yes, please complete D.10. Show on map if applicable.
7 | Provide project map. Include location of project, project benefit and/or service area, and other applicable information.
8. Funding Category:
DAC Implementation Project
General Implementation Project
9. Project Type: | [5 empty] | Other:
Select most applicable project type. See Section II.C. of the 2019 Guidelines for full description of eligible project types. If "Other" is selected, please write in the space provided the proposed project type.
B. | SELECTED ELIGIBILITY REQUIREMENTS
1 | Will the project be included in the IRWM Plan, that will be adopted prior to anticipated Agreement Execution?
|  | Yes | No
2 | Does the project address a critical need(s) and/or priority(ies) of the IRWM Region as identified in the IRWM Plan?
|  | Yes | No | If yes, complete part a:
a. | What IRWM Plan goal(s)/objective(s) does the project address? Identify and explain.
• Obj A: The Project is based on continued collaboration between FPUD and Camp Pendleton, sharing water resources from the Lower Santa Margarita River Basin as well as groundwater recharge and recovery facilities. • Obj B: Upon completing the Pilot Project, a public outreach and education effort will be made to transfer results and knowledge gained to the community and water reuse industry. • Obj C: Data obtained during the Project will be shared through the San Diego Regional Project Database. • Obj D: The Pilot Project will increase scientific knowledge and understanding of water management by addressing the feasibility of effectively treating reclaimed water for potable reuse in the Lower Santa Margarita River Basin without the use of reverse osmosis before application to live stream discharge and ground water basin infiltration. If the Pilot Project shows full-scale IPR is feasible, full-scale implementation would: • Obj E: Increase local supply reliability and reduce dependence on imported water supplies. • Obj F: Increase water supply diversity by creating a new source of water and improve operational flexibility through the increased utilization of Santa Margarita River Conjunctive Use Project (SMRCUP) facilities.
3 | Does the project have an expected useful life consistent with Government Code §16727 (generally 15 years)? If not, explain why this requirement is not applicable.
N/A – this is a pilot project and therefore falls under the category of Decision Support Tool, which is not subject to the 15-year minimum project life. If a full-scale project is deemed feasible as an outcome of this pilot project, the full-scale project would have a greater than 15-year project life.
4 | Does the project address and/or adapt to the effects of climate change? Does the project address the climate change vulnerabilities assessed in the IRWM Plan?
|  | Yes | No | If yes, please explain below.
Reverse osmosis as a treatment process for IPR is highly energy intensive, with significant energy use associated with the execution of the process itself and waste disposal. By using a less energy intensive process such as biological activated carbon filtration, significant energy savings could be made, reducing the amount of greenhouse gases in the atmosphere. Increased energy efficiency will also be achieved by increasing local supply and reducing demand for imported supplies. This pilot project explores the feasibility of a new supply to support a community that is dependent on groundwater and surface water flows, the availability of which is expected to vary because of climate change. The project would address the following climate change vulnerabilities related to water supply from the San Diego IRWM Plan if full-scale IPR is determined feasible: • Very High: Decrease in imported supply. • High: Lack of groundwater storage to buffer drought – the Project would increase groundwater storage. • Medium: Decrease in groundwater supply – the Project would reduce concerns of decreasing groundwater supply. • Very Low: Limited ability to meet summer demand – the Project would produce water year-round
5 | Does the project contribute to regional water self-reliance?
|  | Yes | No | If yes, please explain below.
This is a pilot project intended to determine the optimum process and financial feasibility of full-scale implementation. If full-scale IPR is determined feasible, the project would supply between 10% and 20% of both FPUD’s and Camp Pendleton’s current demands. Any water supplied locally offsets the need to import water from outside the region.
6 | Does the project provide a benefit that meets at least one of the Statewide Priorities as defined in the 2019 IRWM Grant Program Guidelines?
|  | Yes | No | If yes, please identify below.
7 | Will CEQA be completed within 12 months of Final Award?
Yes
NA, project is exempt under CEQA
NA, not a project under CEQA
NA, project benefits DAC/EDA/Tribe (minimum 75%), or a Tribe is a local project sponsor
No
8 | Will all permits necessary to begin construction be acquired within 12 months of Final Award?
Yes
NA, project benefits DAC/EDA/Tribe (minimum 75%), or a Tribe is a local project sponsor
No
C. | WORK PLAN, BUDGET, and SCHEDULE SUMMARY
1 | Project Description: Provide a brief project description summarizing major components, objectives, goals, and intended outcomes/benefits (quantitative and qualitative).
This pilot project will install two treatment facilities. The first will be located at FPUD’s Fallbrook Water Reclamation Plant where FPUD will determine the optimal dosage and efficacy of treatment options. The second treatment facility will be constructed at Camp Pendleton’s Southern Regional Tertiary Treatment Plant, where Camp Pendleton will determine the optimal dosage and efficacy of microfiltration, ozone addition, biofiltration, hydrogen peroxide addition, and ultraviolet (UV) treatment. Water will also be diverted from the treatment process to conduct off-site soil column filtration testing to determine pathogen removal in native soil. Each location will have a skid-mounted pilot treatment train specifically designed to address water quality needs of each plant’s effluent. Each treatment facility would produce approximately 32 AFY (64 AFY total). FPUD will develop a testing protocol to look at nutrient uptake through the discharge in Fallbrook Creek, which will include sampling of the effluent and testing. Camp Pendleton will conduct a tracer test at the Upper Ysidora Subbasin of the Santa Margarita Groundwater Basin. Existing monitoring and production wells will be used to map the vertical and horizontal distribution of the tracer. The project will evaluate pilot treatment equipment including a microfiltration system, ozone dosing system, biofiltration unit, hydrogen peroxide dosing system, and UV dosing system. Source water for the pilot will be from a portion of the effluent stream from the two existing wastewater treatment facilities. After processing and testing, the water will be diverted back to FPUD’s and Camp Pendleton’s existing recycled water systems. Should the pilot project demonstrate feasibility and supports permitting for full-scale implementation, a future full-scale project would provide up to 1,770 AFY potable water.
2 | Budget: Provide cost estimates for each Budget Category listed in the table below. (Required for Pre-Application Material Submittal; not required for Final Application Submittal)
Table 1 - Project Budget
Category |  |  | (a) |  | (b) |  | (c) | (c) | (d)
|  |  | Cost Share: Non‐ State Fund Source |  | Requested Grant Amount |  | Other Cost Share (including other State Sources) |  | Total Cost
(a) | Project Administration |  | 28800 |  | 0 |  | 8760 |  | 37560
(b) | Land Purchase/ Easement |  | 0 |  | 0 |  | 0 |  | 0
(c) | Planning/Design /Engineering /Environmental Documentation |  | 81800 |  | 3600 |  | 0 |  | 85400
(d) | Construction/ Implementation |  | 585700 |  | 683900 |  | 0 |  | 1269600
(e) | Grand Total (Sum rows (a) through (d) for each column) |  | 696300 |  | 687500 |  | 8760 |  | 1392560
Note: Provide information or other documentation to support the cost estimate in a separate attachment. Identify the source of all cost share and other funds. If other funds are not used, describe efforts to obtain other funding and/or why other funding sources were not used.
Match funds: Fallbrook PUD CIP Funds. The approved capital projects budget for FY19-20 includes $350,000 for the Project. Another $350,000 is planned for the following fiscal year, which starts in July 2020. The CIP funds allocated to the project are slightly higher than the anticipated project budget to cover a small contingency if needed.
3 | Cost Share Waiver Requested (DAC or EDA)? |  |  |  |  | Yes | No | If yes, continue below:
Cost Share Waiver Justification: Describe what percentage of the proposed project area encompasses a DAC/EDA, how the community meets the definition of a DAC/EDA, and the need of the DAC/EDA that the project addresses. In order to receive a cost share waiver, the applicant must demonstrate that the project will provide benefits (minimum 25% by population or geography) that address a need of a DAC and/or EDA.
A cost share waiver is not requested for this project because sufficient non-state funding match is available. The project area is 84% DAC by geography and 85% DAC by population.
4 | Schedule: Include reasonable estimates of the start and end dates for each Budget Category listed in Table 1 - Project Budget. (Required for Pre-Application Material Submittal; not required for Final Application Submittal)
Table 2 - Project Schedule
Category |  |  |  |  | (a) Start Date |  |  | (b) End Date
(a) | Direct Project Administration |  |  |  | 2020-03-01 |  |  | 2021-12-31
(b) | Land Purchase/ Easement |  |  |  | N/A |  |  | N/A
(c) | Planning/Design/Engineering/Environmental Documentation |  |  |  | 2020-03-01 |  |  | 2020-09-30
(d) | Construction/ Implementation |  |  |  | 2020-09-01 |  |  | 2021-10-01
D. | OTHER PROJECT INFORMATION
1 | Provide a narrative for project justification. If applicable, include references to supporting documentation such as models, studies, engineering reports, etc. Include any other information that supports the justification for this project, including how the project can achieve the claimed level of benefits.
This project is part of the Santa Margarita Conjunctive Use Project, which is designed to resolve water supply conflicts for users of the Santa Margarita River (including environmental uses), support supply availability and reliability, and protect water supplies from rising costs. Additionally, because Camp Pendleton is downstream of FPUD, and their supply is affected by water availability and quality in the Santa Margarita River, it is critical for both parties to coordinate on this project. Both currently operate water reclamation plants within the Lower Santa Margarita River Basin which discharge treated effluent to the ocean. If the treated effluent were to be diverted to the existing Upper Ysidora Percolation Ponds, it could be utilized as IPR. The proposed pilot project will determine the most effective treatment process for and feasibility of utilizing reclaimed water currently discharged to the ocean as indirect potable reuse. Currently, during extended dry periods, both parties (not just FPUD) would need imported water. This project is to improve water reliability for both Camp Pendleton and FPUD. Camp Pendleton relies 100% on local water from the Santa Margarita River. This project is a key component in creating drought proof water security for Camp Pendleton. Creating water security for Camp Pendleton is critical to ensuring water availability does not negatively impact critical military training activities. The pilot project will produce 64 AFY for testing the proposed IPR approach, providing the framework and justification for full-scale implementation that would provide up to 1,770 AFY water suitable for indirect potable reuse. This pilot project was developed based on a series of technical and feasibility studies completed by FPUD and Camp Pendleton between 2012 and 2018, that support the potential of the basin to support 1,770 AFY recharge for potable reuse (i.e., targeted full-scale implementation). This pilot project would be part of the final planning phases for full-scale implementation and would provide the data and understanding necessary to support permitting and development of a full-scale project. Results from this project will be shared with the community and water reuse industry through a public outreach and education effort. This project also includes preparation of presentation materials to share at future conferences that share the lessons-learned and outcomes of the pilot project, and the feasibility of using a most-cost effective approach to implement IPR than current practices. Feasibility studies completed in support of the project include the 2018 Conceptual Report – Indirect Potable Reuse in the Lower Santa Margarita River Basin, prepared for the Water Resources Division of Camp Pendleton.
2 | Project Benefits Table:
Table 3 - Project Benefits
Anticipated Useful Life of Project (years): |  |  |  |  | N/A – Project is a Decision Support Tool
Primary (Required)
Type of Benefit Claimed: | [6 empty] | Benefit Units*:
Secondary (Optional)
Type of Benefit Claimed: | [6 empty] | Benefit Units*:
Physical Benefits (At project completion or lifetime, as appropriate)
(a) |  |  | (b) |  |  |  | (c)
Benefit |  |  | Added Physical Benefit Description |  |  |  | Quantitative Benefit
Primary |  |  | Create new water supply, increase local groundwater supply and reduce dependency on imported water. |  |  |  | 64 AFY of water produced through the Pilot Project
Secondary |  |  | N/A |  |  |  | N/A
Qualitative Benefits (For Decision Support Tools, please describe non-physical benefits.)
The pilot project will produce 64 AFY. The purpose of the project is to determine if full-scale implementation is feasible (technological and regulatory) and cost-effective. If shown to be viable, full-scale implementation would produce approximately 1,770 AFY (between 10% and 20% of both agencies’ demand). Full-scale IPR would improve water supply reliability by decreasing reliance on imported water and increasing efficiency by maximizing use of existing and planned facilities. By expanding use of recycled water through potable reuse, fewer surface water diversions will be necessary, and the groundwater basin will be recharged, protecting the health of riparian habitats and vulnerable species in the basin, including Arroyo Toad, Least Bell’s Vireo, Southwestern Willow Flycatcher, and steelhead. If full-scale implementation is pursued, the project will also support climate resiliency. Reverse osmosis is highly energy intensive. By using a less energy intensive process such as biological activated carbon filtration, significant energy savings could be made, reducing the amount of greenhouse gases in the atmosphere. Increased energy efficiency will also be achieved by reducing demand for imported supplies. As climate change increases evapotranspiration rates and drought frequency, increased reliance on recycled water is necessary to maintain ecosystem and public health. Information learned would be shared with the wider water industry and could support other regions looking to implement alternative approaches for IPR.
Comments: [Include narrative on additional benefits, as warranted.]
N/A
* | DWR may require applicant to convert or modify Benefit Claimed and/or Benefit Units. Where applicable, select one of the following units that corresponds to the benefit claimed: • For water supply produced, saved, or recycled, enter acre-feet per year (AFY) • For water quality, enter constituent concentration reduced in mg/L • For flood damage reduction, enter inundated acres reduced in acres • For habitat improved, restored or protected, enter habitat restored in acres • For fishery benefits, enter increased fishery flow rate in cubic feet per second (cfs) • For species protection, enter number of species benefited
3 | Does the proposed project provide benefits to multiple IRWM regions [or funding areas]? If the project is located in another funding area, please provide the information requested in the 2019 Guidelines, Section 1.A.
|  | Yes | No | If yes, provide a description of the benefits to the various regions.
N/A
4 | Provide a narrative on cost considerations. For example, were other alternatives to achieve the same types and amounts of physical benefits as the proposed project evaluated? Provide a justification as to why the project was selected (e.g., if the proposed project is not the lowest cost alternative, why is it the preferred alternative? Are there any other advantages that the proposed project provides from a cost perspective?)
The purpose of this pilot project is to determine if full-scale IPR would be more cost effective than current supply options to meet the identified water supply and supply reliability needs of FPUD and Camp Pendleton. The project will allow FPUD to test the process and equipment before committing to full-scale IPR. The primary alternative to the project is to continue purchasing imported water, which currently costs $1,200 to $1,400 per AF for SDCWA member agencies and is expected to double in the next ten years. Traditional reverse osmosis IPR is another alternative and construction can cost anywhere from $3 billion for 93,000 AFY (Pure Water San Diego) to $528 million for 12,890 AFY (East County Advanced Water Purification). These project examples are substantially larger than full-scale implementation for FPUD and Camp Pendleton, which allows for greater efficiency of scale when considering a cost-per-acre-foot. The design feasibility study that will be completed with this project will compare the cost of IPR in comparison to other alternatives.
5 | a. Does the project address a contaminant listed in AB 1249?
|  | Yes | No | If yes, complete parts b and c:
b. Describe how the project helps address the contamination.
N/A
c. Does the project provide safe drinking water to a small disadvantaged community?
|  | Yes | No | If yes, provide an explanation on how the project benefits a small disadvantaged community as defined in the 2019 IRWM Guidelines.
N/A – Although a portion of the benefit area is a DAC, it does not meet the definition of a small DAC (<10,000 people).
6 | Does the project provide safe, clean, affordable, and accessible water adequate for human consumption, cooking, and sanitary purposes (consistent with AB 685) to meet a specific need(s) of a community?
|  | Yes | No | If yes, please describe.
N/A – this is a pilot project and will be used to support permitting of a full-scale project if deemed feasible following the pilot. As such, it would not be able to acquire the appropriate permits to use water produced by the pilot to serve potable demands, but would support future full-scale project that would provide water that could be used for human consumption, cooking, and sanitary purposes consistent with AB 685.
7 | Does the project employ new or innovative technologies or practices, including decision support tools that support the integration of multiple jurisdictions, including, but not limited to, water supply, flood control, land use, and sanitation?
|  | Yes | No | If yes, please describe.
The pilot project will employ an innovative technology to increase scientific knowledge and understanding of water management by addressing the feasibility of effectively treating reclaimed water for potable reuse in the Lower Santa Margarita River Basin without the use of reverse osmosis before application to live stream discharge and ground water basin infiltration. To-date, livestream discharge for IPR without the use of reverse osmosis has not been permitted in the region. This project seeks to demonstrate the feasibility and safety of the proposed approach.
8 | If the project provides benefits (75% by population or geography) to a DAC, explain the need of the DAC and how the project will address the described need. Explain how the area/community meets the definition of a DAC.
No, this project does not provide benefits to at least 75% DAC. FPUD is 17% DAC by geography and 69% DAC by population. The pilot project would not provide water for use because it is a pilot but would support future implementation of full-scale IPR which would serve some DACs, including Camp Pendleton. The project would only result in full-scale implementation if it demonstrates that IPR can be provided at a lower cost than other supply options, which would support affordable water, a particular concern of DACs. However, the project does not meet the 75% DAC threshold to be considered a DAC project.
9 | If the project provides benefits (75% by population or geography) to an EDA, explain the need of the EDA and how the project will address the described need. Explain how the area/community meets the definition of an EDA.
No, this pilot project does not provide benefits to at least 75% EDA during this time. 75% of the pilot project service area population meets the criteria for an EDA and if the results of the pilot project show that IPR water can be treated and delivered at a lower cost than imported water supplies, full-scale implementation would alleviate cost/rate increases for the entire FPUD service area.
10 | If the project provides benefits (75% by population or geography) to a Tribe or a Tribe is the sponsor of the project, explain the need of the Tribe and how the project will address the described need.
N/A – the Project does not serve a Tribe
11 | Does the project sponsor have legal access rights, easements, or other access capabilities to the property to implement the project?
|  | Yes | If yes, please describe.
|  | NA | If NA, please describe why physical access to a property is not needed.
|  | No | If no, please provide a clear and concise narrative with a schedule to obtain necessary access.
No additional land or easements are required. Project footprint is within existing rights-of-way at existing treatment facilities and percolation ponds.
E. | ENVIRONMENTAL
1 | Please fill out the CEQA Timeline Table below, if applicable:
Table 4 - CEQA Timeline
CEQA STEP |  |  |  |  | COMPLETE? (y/n) |  |  | ESTIMATED DATE TO COMPLETE
|  | Initial Study |  |  | N/A |  |  | N/A
|  | Notice of Preparation |  |  | N/A |  |  | N/A
|  | Draft EIR/MND/ND |  |  | N/A |  |  | N/A
|  | Public Review |  |  | N/A |  |  | N/A
|  | Final EIR/MND/ND |  |  | N/A |  |  | N/A
|  | Adoption of Final EIR/MND/ND |  |  | N/A |  |  | N/A
|  | Notice of Determination |  |  | Yes |  |  | 2018-11-15
a. If additional explanation or justification of the timeline is needed, please describe below (optional).
A Notice of Exemption was filed for FPUD and a Categorial Exclusion for Camp Pendleton in November 2018.
2 | Permit Acquisition Plan:
List all permits needed to complete the project. If the project does not provide benefits to a DAC, EDA, or Tribe (min 75%), all permits needed to begin construction must be acquired within 12 months of Final Award.
No. |  | Type of Permit |  |  | Permitting Agency |  |  | Date Acquired or Anticipated
1 |  | Discharge Permit |  |  | RWQCB |  |  | 2020-08-30
2
3
4
5
6
n.
For each permit not yet acquired, describe the following:
No. |  | a. Actions taken to date (include dates of any key meetings, consultations, submittals, etc.) |  |  |  | b. Any issues or obstacles that may delay acquisition of permit
1 |  | RFP issued 11/4/19 to consultant to prepare discharge permit application for tracer testing. |  |  |  | None anticipated
2
3
4
5
n.
3 | Permitting Checklist: This checklist is provided as a courtesy for documentation purposes. Not all permits which may apply are listed. (Required for Pre-Application Material Submittal; not required for Final Application Submittal)
a. | Does the project involve any activities that may affect federally or state listed threatened or endangered species or their critical habitat that are known, or have a potential, to occur on-site, in the surrounding area, or in the service area? (i.e. Federal Endangered Species Act Section 7 Consultation and Incidental Take Authorization and Section 10 Incidental Take Permit, California Endangered Species Act Permit, and/or ESA & CESA Consistency Determination)
|  | Yes | No | If yes, please explain:
N/A
b. | Would the proposed project work in, over, or under navigable waters of the US or discharge dredged or fill material in waters of the US? (i.e. Rivers & Harbors Act Section 10 Permit and/or Clean Water Act Section 404 Permit)
|  | Yes | No | If yes, please explain:
N/A
c. | Will the proposed project have the potential to affect historical, archaeological, or cultural resources? (i.e. National Historic Preservation Act and/or State Historic Preservation Officer Consultation)
|  | Yes | No | If yes, please explain:
N/A
d. | Will the proposed project discharge into a water of the US? (i.e. Clean Water Act Section 401 and/or 404 Permit)
|  | Yes | No | If yes, please explain:
One goal of the Project is to determine the feasibility of and requirements to discharge into the Fallbrook Creek based on the water quality produced by the Pilot Project. However, the Pilot Project will not discharge into the creek.
e. | Will the proposed project divert the natural flow of a river, stream, or lake? (i.e. Lake or Streambed Alteration Agreement)
|  | Yes | No | If yes, please explain:
N/A
f. | Will the proposed project change the bed, channel, or bank of a river, stream, or lake? (i.e. Lake or Streambed Alteration Agreement)
|  | Yes | No | If yes, please explain:
N/A
g. | Will the proposed project use any material from the bed, channel, or bank of a river, stream, or lake? (i.e. Lake or Streambed Alteration Agreement)
|  | Yes | No | If yes, please explain:
N/A
h. | Will the proposed project deposit or dispose of debris, waste, or other material containing crumbled, flaked, or ground pavement where it can pass into a river, stream, or lake? (i.e. Lake or Streambed Alteration Agreement/National Pollutant Discharge Elimination System Permit/Waste Discharge Requirements Permit)
|  | Yes | No | If yes, please explain:
N/A
i. | For water supply projects, do you need to obtain a water right? (Water Rights Permit)
|  | Yes | No | If yes, please explain:
N/A
j. | Is the proposed project within the defined coastal zone? (Coastal Development Permit)
|  | Yes | No | If yes, please explain:
N/A

## Answers (hidden)
A. PROJECT INFORMATION
1
2
3
4
5
6
7
8
9

## List Values (hidden)
Eligible Applicant Type | IRWM Regions | Project Type | Benefit Claimed | Benefit Units | Statewide Priorities
| American River Basin |  |  |  | 1. Make Conservation a California Way of Life
Public Agency | Antelope Valley | Conjunctive use | Ecosystem Restoration | acre(s) | 2. Increase Regional Self-Reliance and Integrated Water Management Across All Levels of Government
Non-profit Organization | Anza Borrego Desert | Decision support tool | Ecosystem/Freshwater habitat | AFY | 3. Achieve the Co-Equal Goals for the Delta
Public Utility | Coachella Valley | Groundwater aquifer cleanup | Fishery Improvements | cfs | 4. Protect and Restore Important Ecosystems
Federally Recognized Indian Tribe | Cosumnes, American, Bear, Yuba (CABY) | Other | Flood Damage Reduction | mg/L | 5. Manage and Prepare for Dry Periods
Indian Tribe listed on the Native American Heritage Commission’s California Tribal Consultation List | East Contra Costa County | Recharge project | Flood Management | Other | 6. Expand Water Storage Capacity and Improve Groundwater Management
Mutual Water Company | East Stanislaus | Stormwater management | Groundwater Recharge |  | 7. Provide Safe Water for All Communities
| Eastern San Joaquin | Surface storage | Habitat Restoration |  | 8. Increase Flood Protection
| Fremont Basin | Underground water storage | Operational Efficiency |  | 9. Increase Operational and Regulatory Efficiency
| Greater Los Angeles County | Water conservation | Grant Admin |  | 10. Identify Sustainable and Integrated Financing Opportunities
| Greater Monterey County | Water conveyance facility | Reduce Groundwater Pumping |  |  | ListBox Option
| Imperial | Water desalination | Flood Protection
| Inyo-Mono | Water quality | Stormwater Management
| Kaweah River Basin | Water recycling | Streamflow Restoration
| Kern County | Water reuse | Water Conservation
| Kings Basin Water Authority | Watershed project | Water Quality
| Lahontan Basins | Water-use efficiency | Water Quality - Groundwater
| Madera |  | Water Quality - Sediment
| Merced |  | Water Quality - Surface Water
| Mojave |  | Water Supply - Groundwater
| Mokelumne/Amador/Calaveras (MAC) |  | Water Supply - Recycled Water
| Monterey Peninsula, Carmel Bay, So. Monterey Bay |  | Water Supply - Surface Water
| North Coast |  | Water Supply Reliability
| North Sacramento Valley |  | Other
Pajaro River Watershed
Poso Creek
San Diego
San Francisco Bay Area
San Gorgonio
San Luis Obispo
Santa Ana River Watershed
Santa Barbara County
Santa Cruz County
South Orange County Watershed Management Area
Southern Sierra
Tahoe-Sierra
Tule River Basin
Tuolumne-Stanislaus
Upper Feather River Watershed
Upper Pit River Watershed
Upper Sacramento-McCloud
Upper Santa Clara River
Upper Santa Margarita
Watersheds Coalition of Ventura County
Westside (Yolo, Solano, Napa, Lake, Colusa)
Westside-San Joaquin
Yosemite-Mariposa
Yuba County